## BLANK Gantt Chart & Burndown
SCRUM PROJECT MANAGEMENT GANTT CHART
GANTT CHART AND BURNDOWN
[9 empty] | SPRINTS | SPRINT 1
SPRINT 2
SPRINT 3
SPRINT 4
SPRINT 5
SPRINT 5
WORK BREAKDOWN STRUCTURE | TASK TITLE | TASK OWNER | AMOUNT OF WORK IN HOURS |  |  | SPRINT | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
|  |  | ESTIMATE | COMPLETED | REMAINING | [5 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project formalization |  | 28 | 30 | -2 | 1 |  |  |  | 107.1%
| Ideas brainstorming | Everyone | 4 | 4 | 0 | 1 | 2022-10-10 | 2022-10-12 | 3 | 100% | bar: WEEK 1 M to WEEK 1 W
| Research of information | Everyone | 6 | 6 | 0 | 1 | 2022-10-12 | 2022-10-14 | 3 | 100% | bar: WEEK 1 W to WEEK 1 F
| Project planning | Everyone | 9 | 11 | -2 | 1 | 2022-10-12 | 2022-10-18 | 7 | 122.2% | bar: WEEK 1 W to WEEK 2 T
| Scope and goal settings | Everyone | 4 | 4 | 0 | 1 | 2022-10-18 | 2022-10-18 | 1 | 100% | bar: WEEK 2 T
| Technical architecture sketching | Everyone | 3 | 3 | 0 | 1 | 2022-10-18 | 2022-10-19 | 2 | 100% | bar: WEEK 2 T to WEEK 2 W
| Project proposal | Everyone | 2 | 2 | 0 | 1 | 2022-10-20 | 2022-10-20 | 1 | 100% | bar: WEEK 2 R
2 | Project draft |  | 16 | 15 | 1 | 2 |  |  |  | 93.75%
| User stories | Everyone | 4 | 4 | 0 | 2 | 2023-02-20 | 2023-02-21 | 2 | 100% | bar: WEEK 3 M to WEEK 3 T
| Mockups | Everyone | 6 | 5 | 1 | 2 | 2023-02-21 | 2023-02-22 | 2 | 83.33% | bar: WEEK 3 T to WEEK 3 W
| Function point & CoCoMo | Everyone | 4 | 4 | 0 | 2 | 2023-02-23 | 2023-02-23 | 1 | 100% | bar: WEEK 3 R
| Product backlog | Everyone | 2 | 2 | 0 | 2 | 2023-02-24 | 2023-02-24 | 1 | 100% | bar: WEEK 3 F
| Documentation | Everyone | 2 | 2 | 0 | 2 | 2023-02-24 | 2023-02-24 | 1 | 100% | bar: WEEK 3 F
3 | Back-end & API Gateway |  | 16 | 19 | -3 | 3,4,5 |  |  |  | 118.8%
| FastAPI initial setup | Everyone | 7 | 7 | 0 | 3 |  |  | 1 | 100%
| Kong Gateway initial setup | Everyone | 7 | 10 | -3 | 3 |  |  | 1 | 142.9%
| Neo4j & Firebase initial setup | Everyone | 2 | 2 | 0 | 3 |  |  | 1 | 100%
| Social microservice 1st version |  |  |  | 0 | 3 |  |  | 1 | #DIV/0!
| Firebase microservice |  |  |  | 0 | 3 |  |  | 1 | #DIV/0!
| DeepDetect initial setup |  |  |  | 0 | 4 |  |  | 1 | #DIV/0!
| Elasticsearch & Kibana initial setup |  |  |  | 0 | 4 |  |  | 1 | #DIV/0!
| Search microservice |  |  |  | 0 | 4 |  |  | 1 | #DIV/0!
| Images indicization microservice |  |  |  | 0 | 4 |  |  | 1 | #DIV/0!
| Social microservice 2nd version |  |  |  | 0 | 4 |  |  | 1 | #DIV/0!
| RabbitMQ initial setup through CloudAMQP |  |  |  | 0 | 5 |  |  | 1 | #DIV/0!
| Notifications microservice |  |  |  | 0 | 5 |  |  | 1 | #DIV/0!
| Social microservice final version |  |  |  | 0 | 5 |  |  | 1 | #DIV/0!
4 | Front-end |  | 5 | 7 | -2 | 2,3,4,5,6 |  |  |  | 140%
| React initial setup | Everyone | 4 | 6 | -2 | 2 | 2023-02-27 | 2023-02-28 | 2 | 150% | bar: WEEK 4 M to WEEK 4 T; WEEK 10 M
| Welcome page |  | 1 | 1 | 0 | 2 | 2023-03-01 | 2023-03-01 | 1 | 100% | bar: WEEK 4 W
| Sign-in page |  |  |  | 0 | 2 | 2023-03-01 | 2023-03-02 | 2 | #DIV/0! | bar: WEEK 4 W to WEEK 4 R
| Forgot password page |  |  |  | 0 | 2 |  |  | 1 | #DIV/0!
| Sign-up page |  |  |  | 0 | 2 | 2023-03-01 | 2023-03-02 | 2 | #DIV/0! | bar: WEEK 4 W to WEEK 4 R
| Homepage |  |  |  | 0 | 2 | 2023-03-03 | 2023-03-03 | 1 | #DIV/0! | bar: WEEK 4 F
| App-bar |  |  |  | 0 | 2 |  |  | 1 | #DIV/0!
| User profile page |  |  |  | 0 | 3 |  |  | 1 | #DIV/0!
| User settings page |  |  |  | 0 | 3 |  |  | 1 | #DIV/0!
| Post page |  |  |  | 0 | 3 |  |  | 1 | #DIV/0!
| New post page |  |  |  | 0 | 3 |  |  | 1 | #DIV/0!
| Search results page |  |  |  | 0 | 4 |  |  | 1 | #DIV/0!
| Comments section |  |  |  | 0 | 4 |  |  | 1 | #DIV/0!
| Notifications section |  |  |  | 0 | 5 |  |  | 1 | #DIV/0!
| Alert pop-ups |  |  |  | 0 | 5 |  |  | 1 | #DIV/0!
| Followers/following section |  |  |  | 0 | 5 |  |  | 1 | #DIV/0!
| Connect to backend through endpoints |  |  |  | 0 | 6 |  |  | 1 | #DIV/0!
5 | Containerization |  | 0 | 0 | 0 | 6 |  |  |  | #DIV/0!
| Dockerfiles creation |  |  |  | 0 | 6 |  |  | 1 | #DIV/0!
| Docker containers setup |  |  |  | 0 | 6 |  |  | 1 | #DIV/0!
| Integrate front-end as docker container |  |  |  | 0 | 6 |  |  | 1 | #DIV/0!
|  |  | ESTIMATE | COMPLETED | REMAINING | DAYS | EST/DAYS
| BURNDOWN DATA | TOTAL HOURS | 65 | 71 | -6 | 60 | 1.0833 |  |  | DAY | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | TOTAL HOURS
[6 empty] | ^ Enter number of days |  |  |  | PLAN | 65 | 63.9167 | 62.8333 | 61.75 | 60.6667 | 59.5833 | 58.5 | 57.4167 | 56.3333 | 55.25 | 54.1667 | 53.0833 | 52 | 50.9167 | 49.8333 | 48.75 | 47.6667 | 46.5833 | 45.5 | 44.4167 | 43.3333 | 42.25 | 41.1667 | 40.0833 | 39 | 37.9167 | 36.8333 | 35.75 | 34.6667 | 33.5833 | 32.5 | 31.4167 | 30.3333 | 29.25 | 28.1667 | 27.0833 | 26 | 24.9167 | 23.8333 | 22.75 | 21.6667 | 20.5833 | 19.5 | 18.4167 | 17.3333 | 16.25 | 15.1667 | 14.0833 | 13 | 11.9167 | 10.8333 | 9.75 | 8.6667 | 7.5833 | 6.5 | 5.4167 | 4.3333 | 3.25 | 2.1667 | 1.0833
[10 empty] | ESTIMATE | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 3900
[9 empty] | Enter hours completed per day ----> | HRS COMPLETED | [60 empty] | 0
[10 empty] | HRS REMAINING | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 3900
CLICK HERE TO CREATE SCRUM PROJECT MANAGEMENT GANTT CHART TEMPLATES IN SMARTSHEET

## Release Backlog
SCRUM PROJECT MANAGEMENT GANTT CHART
RELEASE BACKLOG
PRIORITY | SPRINT | FUNCTIONALITY | TASK TITLE | TASK DESCRIPTION | TASK OWNER | WORK ESTIMATE IN HOURS | STATUS | NOTES | STATUS KEY | WORK ESTIMATE IN HOURS
[6 empty] | 1 | Not Started |  | Not Started | 1
[6 empty] | 2 | In Progress |  | In Progress | 2
[6 empty] | 8 | Completed |  | Completed | 4
[6 empty] | 8 | Not Started |  |  | 8
[6 empty] | 4 |  |  |  | 16
[6 empty] | 80 |  |  |  | 24
[6 empty] | 16 |  |  |  | 40
[6 empty] | 8 |  |  |  | 80
4
2
24
40
8

## User Stories or Tasks
USER STORIES
AS A | I WANT TO | SO THAT I CAN | ADDED BY | DATED ADDED
Guest | Register to the system | Create my profile | Everyone | 2022-10-13
Non-logged registered user | Login into the system | Use system's services | Everyone | 2022-10-13
Logged user | Logout from the system | Login as another user | Everyone | 2022-10-13
Logged user | Access the homepage | Discover the most popular images | Everyone | 2022-10-13
Logged user | Access the homepage | Discover images published by followed users | Everyone | 2022-10-13
Logged user | Search for images | Visualize them | Everyone | 2022-10-13
Logged user | Search for other users | Visualize their profile and their images | Everyone | 2022-10-13
Logged user | Upload an image | Share it with other users | Everyone | 2022-10-13
Logged user | Save an image | Visualize it later on | Everyone | 2022-10-13
Logged user | Remove an uploaded image | Deny to other users to visualize it | Everyone | 2022-10-13
Logged user | Like an image | Express my appreciation about it | Everyone | 2022-10-13
Logged user | Get notified | Know if another user liked or commented one of my image or followed me | Everyone | 2022-10-13
Logged user | Follow another user | Stay updated about his new images | Everyone | 2022-10-13
Logged user | Access my profile | Visualize all my published images | Everyone | 2022-10-13
Logged user | Access my profile | Visualize all my saved images | Everyone | 2022-10-13
Logged user | Access user profile | Visualize followers/followed users | Everyone | 2022-10-13
Logged user | Access my profile settings | Manage it | Everyone | 2022-10-13
Logged user | Visualize image | Visualize its details and comments | Everyone | 2022-10-13
Logged user | Access other user's profile page | Visualize his details and published images | Everyone | 2022-10-13
Logged user | Delete my profile | No longer access the system | Everyone | 2022-10-13