## BLANK Gantt Chart & Burndown
SCRUM PROJECT MANAGEMENT GANTT CHART
GANTT CHART AND BURNDOWN
[9 empty] | SPRINTS | SPRINT 1
SPRINT 2
SPRINT 3
SPRINT 4
SPRINT 5
SPRINT 5
WORK BREAKDOWN STRUCTURE | TASK TITLE | TASK OWNER | AMOUNT OF WORK IN HOURS |  |  | SPRINT | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
|  |  | ESTIMATE | COMPLETED | REMAINING | [5 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project formalization |  | 31 | 33 | -2 | 1 |  |  |  | 106.5%
| Ideas brainstorming | Everyone | 6 | 6 | 0 | 1 | 2022-10-10 | 2022-10-11 | 2 | 100% | bar: WEEK 1 M to WEEK 1 T; WEEK 4 R
| Research of information | Everyone | 6 | 6 | 0 | 1 | 2022-10-12 | 2022-10-14 | 3 | 100% | bar: WEEK 1 W to WEEK 1 F; WEEK 4 R
| Project planning | Everyone | 10 | 12 | -2 | 1 | 2022-10-12 | 2022-10-18 | 7 | 120% | bar: WEEK 1 W to WEEK 2 T; WEEK 4 R
| Scope and goal settings | Everyone | 4 | 4 | 0 | 1 | 2022-10-18 | 2022-10-18 | 1 | 100% | bar: WEEK 2 T; WEEK 4 R
| Technical architecture sketching | Everyone | 3 | 3 | 0 | 1 | 2022-10-19 | 2022-10-19 | 1 | 100% | bar: WEEK 2 W; WEEK 4 R
| Project proposal | Everyone | 2 | 2 | 0 | 1 | 2022-10-20 | 2022-10-20 | 1 | 100% | bar: WEEK 2 R; WEEK 4 R
2 | Project draft |  | 17 | 16 | 1 | 2 |  |  |  | 94.12%
| User stories | Everyone | 4 | 4 | 0 | 2 | 2023-02-06 | 2023-02-07 | 2 | 100% | bar: WEEK 3 M to WEEK 3 T; WEEK 4 R
| Mockups | Everyone | 6 | 5 | 1 | 2 | 2023-02-07 | 2023-02-08 | 2 | 83.33% | bar: WEEK 3 T to WEEK 3 W; WEEK 4 R
| Function point & CoCoMo | Everyone | 4 | 4 | 0 | 2 | 2023-02-09 | 2023-02-09 | 1 | 100% | bar: WEEK 3 R; WEEK 4 R
| Product backlog | Everyone | 3 | 3 | 0 | 2 | 2023-02-10 | 2023-02-10 | 1 | 100% | bar: WEEK 3 F; WEEK 4 R
| Documentation | Everyone | 3 | 3 | 0 | 2 | 2023-02-10 | 2023-02-10 | 1 | 100% | bar: WEEK 3 F; WEEK 4 R
3 | Back-end & API Gateway |  | 40 | 44 | -4 | 3,4,5 |  |  |  | 110%
| FastAPI initial setup | Everyone | 7 | 7 | 0 | 3 | 2023-02-20 | 2023-02-21 | 2 | 100% | bar: WEEK 4 R; WEEK 5 M to WEEK 5 T
| Kong Gateway initial setup | Everyone | 7 | 10 | -3 | 3 | 2023-02-22 | 2023-02-24 | 3 | 142.9% | bar: WEEK 4 R; WEEK 5 W to WEEK 5 F
| Neo4j & Firebase initial setup | Everyone | 4 | 4 | 0 | 3 | 2023-02-27 | 2023-02-27 | 1 | 100% | bar: WEEK 4 R; WEEK 6 M
| Social microservice 1st version | Sisti | 8 | 8 | 0 | 3 | 2023-02-28 | 2023-03-02 | 3 | 100% | bar: WEEK 4 R; WEEK 6 T to WEEK 6 R
| Firebase microservice | Ficorella | 5 | 5 | 0 | 3 | 2023-02-28 | 2023-03-01 | 2 | 100% | bar: WEEK 4 R; WEEK 6 T to WEEK 6 W
| DeepDetect initial setup | Everyone | 9 | 10 | -1 | 4 | 2023-03-06 | 2023-03-08 | 3 | 111.1% | bar: WEEK 4 R; WEEK 7 M to WEEK 7 W
| Elasticsearch & Kibana initial setup | Everyone | 9 | 11 | -2 | 4 | 2023-03-09 | 2023-03-13 | 5 | 122.2% | bar: WEEK 4 R; WEEK 7 R to WEEK 8 M
| Search microservice | Ficorella | 5 | 5 | 0 | 4 | 2023-03-14 | 2023-03-15 | 2 | 100% | bar: WEEK 4 R; WEEK 8 T to WEEK 8 W
| Images indicization microservice | Sisti | 5 | 5 | 0 | 4 | 2023-03-14 | 2023-03-15 | 2 | 100% | bar: WEEK 4 R; WEEK 8 T to WEEK 8 W
| Social microservice 2nd version | Turbessi | 5 | 5 | 0 | 4 | 2023-03-14 | 2023-03-15 | 2 | 100% | bar: WEEK 4 R; WEEK 8 T to WEEK 8 W
| RabbitMQ initial setup through CloudAMQP | Everyone | 8 | 10 | -2 | 5 | 2023-03-20 | 2023-03-22 | 3 | 125% | bar: WEEK 4 R; WEEK 9 M to WEEK 9 W
| Notifications microservice | Sisti, Turbessi | 8 | 11 | -3 | 5 | 2023-03-23 | 2023-03-27 | 5 | 137.5% | bar: WEEK 4 R; WEEK 9 R to WEEK 10 M
| Social microservice final version | Ficorella | 6 | 6 | 0 | 5 | 2023-03-28 | 2023-03-30 | 3 | 100% | bar: WEEK 4 R; WEEK 10 T to WEEK 10 R
4 | Front-end |  | 113 | 123 | -10 | 2,3,4,5,6 |  |  |  | 108.8%
| React initial setup | Everyone | 4 | 6 | -2 | 2 | 2023-02-13 | 2023-02-14 | 2 | 150% | bar: WEEK 4 M to WEEK 4 T; WEEK 4 R; WEEK 10 M
| Welcome page | Ficorella | 2 | 2 | 0 | 2 | 2023-02-15 | 2023-02-16 | 2 | 100% | bar: WEEK 4 W to WEEK 4 R
| Sign-in page | Ficorella | 3 | 3 | 0 | 2 | 2023-02-16 | 2023-02-17 | 2 | 100% | bar: WEEK 4 R to WEEK 4 F
| Forgot password page | Sisti | 3 | 3 | 0 | 2 | 2023-02-15 | 2023-02-16 | 2 | 100% | bar: WEEK 4 W to WEEK 4 R
| Sign-up page | Sisti | 3 | 3 | 0 | 2 | 2023-02-16 | 2023-02-17 | 2 | 100% | bar: WEEK 4 R to WEEK 4 F
| Homepage | Turbessi | 5 | 6 | -1 | 2 | 2023-02-15 | 2023-02-17 | 3 | 120% | bar: WEEK 4 W to WEEK 4 F
| App-bar | Everyone | 3 | 3 | 0 | 2 | 2023-02-17 | 2023-02-17 | 1 | 100% | bar: WEEK 4 R to WEEK 4 F
| User profile page | Ficorella | 5 | 5 | 0 | 3 | 2023-03-02 | 2023-03-03 | 2 | 100% | bar: WEEK 4 R; WEEK 6 R to WEEK 6 F
| User settings page | Sisti | 3 | 3 | 0 | 3 | 2023-03-03 | 2023-03-03 | 1 | 100% | bar: WEEK 4 R; WEEK 6 F
| Post page | Turbessi | 5 | 5 | 0 | 3 | 2023-02-28 | 2023-03-01 | 2 | 100% | bar: WEEK 4 R; WEEK 6 T to WEEK 6 W
| New post page | Turbessi | 4 | 5 | -1 | 3 | 2023-03-02 | 2023-03-03 | 2 | 125% | bar: WEEK 4 R; WEEK 6 R to WEEK 6 F
| Search results page | Ficorella, Sisti | 7 | 7 | 0 | 4 | 2023-03-16 | 2023-03-17 | 2 | 100% | bar: WEEK 4 R; WEEK 8 R to WEEK 8 F
| Comments section | Turbessi | 4 | 4 | 0 | 4 | 2023-03-16 | 2023-03-17 | 2 | 100% | bar: WEEK 4 R; WEEK 8 R to WEEK 8 F
| Notifications section | Ficorella | 3 | 3 | 0 | 5 | 2023-03-30 | 2023-03-31 | 2 | 100% | bar: WEEK 4 R; WEEK 10 R to WEEK 10 F
| Alert pop-ups | Sisti | 2 | 2 | 0 | 5 | 2023-03-29 | 2023-03-30 | 2 | 100% | bar: WEEK 4 R; WEEK 10 W to WEEK 10 R
| Followers/following section | Turbessi | 3 | 3 | 0 | 5 | 2023-03-30 | 2023-03-31 | 2 | 100% | bar: WEEK 4 R; WEEK 10 R to WEEK 10 F
| Connect to backend through endpoints | Everyone | 10 | 10 | 0 | 6 | 2023-04-03 | 2023-04-05 | 3 | 100% | bar: WEEK 4 R; WEEK 11 M to WEEK 11 W
5 | Containerization |  | 22 | 25 | -3 | 6 |  |  |  | 113.6%
| Dockerfiles creation | Everyone | 10 | 13 | -3 | 6 | 2023-04-06 | 2023-04-10 | 5 | 130% | bar: WEEK 4 R; WEEK 11 R to WEEK 12 M
| Docker containers setup | Everyone | 7 | 7 | 0 | 6 | 2023-04-11 | 2023-04-12 | 2 | 100% | bar: WEEK 4 R; WEEK 12 T to WEEK 12 W
| Integrate front-end as docker container | Everyone | 5 | 5 | 0 | 6 | 2023-04-13 | 2023-04-14 | 2 | 100% | bar: WEEK 4 R; WEEK 12 R to WEEK 12 F
|  |  | ESTIMATE | COMPLETED | REMAINING | DAYS | EST/DAYS
| BURNDOWN DATA | TOTAL HOURS | 201 | 216 | -15 | 60 | 3.35 |  |  | DAY | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | TOTAL HOURS
[6 empty] | ^ Enter number of days |  |  |  | PLAN | 201 | 197.65 | 194.3 | 190.95 | 187.6 | 184.25 | 180.9 | 177.55 | 174.2 | 170.85 | 167.5 | 164.15 | 160.8 | 157.45 | 154.1 | 150.75 | 147.4 | 144.05 | 140.7 | 137.35 | 134 | 130.65 | 127.3 | 123.95 | 120.6 | 117.25 | 113.9 | 110.55 | 107.2 | 103.85 | 100.5 | 97.15 | 93.8 | 90.45 | 87.1 | 83.75 | 80.4 | 77.05 | 73.7 | 70.35 | 67 | 63.65 | 60.3 | 56.95 | 53.6 | 50.25 | 46.9 | 43.55 | 40.2 | 36.85 | 33.5 | 30.15 | 26.8 | 23.45 | 20.1 | 16.75 | 13.4 | 10.05 | 6.7 | 3.35
[10 empty] | ESTIMATE | 201 | 198 | 195 | 189 | 184 | 177 | 169 | 161 | 158 | 156 | 156 | 153 | 150 | 147 | 143 | 137 | 135 | 131 | 126 | 119 | 111 | 108 | 104 | 101 | 97 | 94 | 90 | 82 | 75 | 67 | 59 | 56 | 53 | 49 | 46 | 42 | 38 | 30 | 23 | 18 | 12 | 9 | 5 | 2 | -2 | -6 | -9 | -11 | -14 | -20 | -23 | -26 | -30 | -33 | -38 | -42 | -46 | -50 | -53 | -55 | 4098
[9 empty] | Enter hours completed per day ----> | HRS COMPLETED | 3 | 3 | 6 | 5 | 7 | 8 | 8 | 3 | 2 | 0 | 3 | 3 | 3 | 4 | 6 | 2 | 4 | 5 | 7 | 8 | 3 | 4 | 3 | 4 | 3 | 4 | 8 | 7 | 8 | 8 | 3 | 3 | 4 | 3 | 4 | 4 | 8 | 7 | 5 | 6 | 3 | 4 | 3 | 4 | 4 | 3 | 2 | 3 | 6 | 3 | 3 | 4 | 3 | 5 | 4 | 4 | 4 | 3 | 2 | 3 | 259
[10 empty] | HRS REMAINING | 198 | 195 | 189 | 184 | 177 | 169 | 161 | 158 | 156 | 156 | 153 | 150 | 147 | 143 | 137 | 135 | 131 | 126 | 119 | 111 | 108 | 104 | 101 | 97 | 94 | 90 | 82 | 75 | 67 | 59 | 56 | 53 | 49 | 46 | 42 | 38 | 30 | 23 | 18 | 12 | 9 | 5 | 2 | -2 | -6 | -9 | -11 | -14 | -20 | -23 | -26 | -30 | -33 | -38 | -42 | -46 | -50 | -53 | -55 | -58 | 3839
CLICK HERE TO CREATE SCRUM PROJECT MANAGEMENT GANTT CHART TEMPLATES IN SMARTSHEET

## Release Backlog
SCRUM PROJECT MANAGEMENT GANTT CHART
RELEASE BACKLOG
PRIORITY | SPRINT | FUNCTIONALITY | TASK TITLE | TASK DESCRIPTION | TASK OWNER | WORK ESTIMATE IN HOURS | STATUS | NOTES | STATUS KEY | WORK ESTIMATE IN HOURS
[6 empty] | 1 | Not Started |  | Not Started | 1
[6 empty] | 2 | In Progress |  | In Progress | 2
[6 empty] | 8 | Completed |  | Completed | 4
[6 empty] | 8 | Not Started |  |  | 8
[6 empty] | 4 |  |  |  | 16
[6 empty] | 80 |  |  |  | 24
[6 empty] | 16 |  |  |  | 40
[6 empty] | 8 |  |  |  | 80
4
2
24
40
8

## User Stories or Tasks
USER STORIES
AS A | I WANT TO | SO THAT I CAN | ADDED BY | DATED ADDED
Guest | Register to the system | Create my profile | Everyone | 2022-10-13
Non-logged registered user | Login into the system | Use system's services | Everyone | 2022-10-13
Logged user | Logout from the system | Login as another user | Everyone | 2022-10-13
Logged user | Access the homepage | Discover the most popular images | Everyone | 2022-10-13
Logged user | Access the homepage | Discover images published by followed users | Everyone | 2022-10-13
Logged user | Search for images | Visualize them | Everyone | 2022-10-13
Logged user | Search for other users | Visualize their profile and their images | Everyone | 2022-10-13
Logged user | Upload an image | Share it with other users | Everyone | 2022-10-13
Logged user | Save an image | Visualize it later on | Everyone | 2022-10-13
Logged user | Remove an uploaded image | Deny to other users to visualize it | Everyone | 2022-10-13
Logged user | Like an image | Express my appreciation about it | Everyone | 2022-10-13
Logged user | Get notified | Know if another user liked or commented one of my image or followed me | Everyone | 2022-10-13
Logged user | Follow another user | Stay updated about his new images | Everyone | 2022-10-13
Logged user | Access my profile | Visualize all my published images | Everyone | 2022-10-13
Logged user | Access my profile | Visualize all my saved images | Everyone | 2022-10-13
Logged user | Access user profile | Visualize followers/followed users | Everyone | 2022-10-13
Logged user | Access my profile settings | Manage it | Everyone | 2022-10-13
Logged user | Visualize image | Visualize its details and comments | Everyone | 2022-10-13
Logged user | Access other user's profile page | Visualize his details and published images | Everyone | 2022-10-13
Logged user | Delete my profile | No longer access the system | Everyone | 2022-10-13